## TestCase_UI
ID | Test Scenario | Preconditions | Steps | Expected Result | Actual Result | Status | Comments | Screenshot
TC001 | Sign up - valid credentials | User not registered | 1. Open Signup modal/page 2. Enter unique username and valid password 3. Click "Sign up" | Account created successfully; success message displayed; user can login with new credentials. | Account created successfully; success message displayed; user can login with new credentials. | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC002 | Sign up - password rules (boundary & variations) | User not registered | 1. Open Signup 2. Enter username 3. Enter passwords: - Min -1 (7 chars) → should fail - Min (8 chars) → should pass - Min +1 (9 chars) → should pass - Max -1 (19 chars) → should pass - Max (20 chars) → should pass - Max +1 (21 chars) → should fail 4. Click "Sign up" | Passwords outside 8–20 chars rejected with validation messages; valid lengths accepted | Successfully signed up with 7 characters (below min); validation messages not shown Note: sign up with 7 chars test executed | Fail BUG-001 | Tested on Chrome 115, Windows 10. Username: TestUser81 Password: 1234567 Note: Boundary tests not fully executed for portfolio | Screenshots/UI/BUG-001_TC_005_Successful_sign_up_below_min_chars.PNG
TC003 | Sign up - password character rules | User not registered | 1. Open Signup 2. Enter username 3. Enter passwords violating rules: - Missing uppercase - Missing lowercase - Missing digit - Missing special character - Containing spaces 4. Click "Sign up" | Signup rejected; validation messages shown for each violated rule | Successfully signed up with missing required characters; validation messages not shown | Fail BUG-002 | Tested on Chrome 115, Windows 10. Username: TestUser81 Password: 1234567 Note: Partial execution; portfolio practice | Screenshots/UI/BUG-002_TC_003_Successful_sign_up_missing_required_characters.PNG
TC004 | Sign up - existing username | User registered with valid credentials | 1. Open Signup 2. Enter username that already exists 3. Enter password 4. Click "Sign up" | Error message shown: "User already exists" or application-specific message; signup rejected | Error message shown: "This user already exists"; signup rejected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC005 | Sign up - empty username | User not registered | 1. Open Signup 2. Leave username empty 3. Enter password 4. Click "Sign up" | Error message shown: "Please fill out Username and Password"; signup rejected | Error message shown: "Please fill out Username and Password"; signup rejected | Pass | Tested on Chrome 115, Windows 10. Username: Password: 123321Mk! | N/A
TC006 | Sign up - empty password | User not registered | 1. Open Signup 2. Enter username 3. Leave password empty 4. Click "Sign up" | Error message shown: "Please fill out Username and Password"; signup rejected | Error message shown: "Please fill out Username and Password"; signup rejected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: | N/A
TC007 | Sign up - SQL Injection - like or invalid characters | User not registered | 1. Enter username containing test SQL-like chars (e.g., or_1_eq_1_test2) 2. Click "Sign up" | App sanitizes input; rejects invalid username; no server errors or DB injection | Successfully signed up with username containing special SQL Injection - like chars | Fail BUG-003 | Tested on Chrome 115, Windows 10 Username: or_1_eq_1_test2 Password: 12345678 | Screenshots/UI/BUG-003_TC_007_Successful_sign_up_SQL_Injection.PNG
TC008 | Login - valid credentials | User registered with valid credentials | 1. Go to Login page 2. Enter valid username 3. Enter valid password 4. Click "Login" | User successfully logged in and redirected to dashboard/home | User successfully logged in and redirected to dashboard/home | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC009 | Login - invalid credentials | User registered with valid credentials | 1. Go to Login page 2. Enter invalid username or invalid password 3. Click "Login" | Error message shown: "User doesn't exist" or "Invalid password" Log in rejected. | 1. When entered invalid username, error message shown: "User doesn't exist". Log in rejected. 2. When entered invalid password, error message shown: "Invalid password". Log in rejected. | Pass | Tested on Chrome 115, Windows 10. 1. Invalid username test: Username: TestUser8000 Password: 123321Mk! 2. Invalid password test: Username: TestUser80 Password: 123321Mk!+ | N/A
TC010 | Login - empty username or password | User registered with valid credentials | 1. Go to Login page 2. Leave username or password empty 3. Click "Login" | Error message shown: "Please fill out Username and Password" Log in rejected. | When username or password left empty, error message shown: "Please fill out Username and Password" Log in rejected. | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC011 | Login - password boundary rules | User registered with valid credentials; password rules enforced | 1. Go to Login page 2. Enter password variations: - Min -1 (7 chars) → fail - Min (8 chars) → pass - Min +1 (9 chars) → pass - Max -1 (19 chars) → pass - Max (20 chars) → pass - Max +1 (21 chars) → fail 3. Click "Login" | System rejects passwords outside boundaries; login allowed within allowed range | Not tested. Please, see comments. | Not executed | Tests not executed because signup validations already failed; any invalid credentials would not pass login, so testing is redundant. Will be tested after sign-up bugs (BUG-001, BUG-002) are fixed and retested successfully. | N/A
TC012 | Login - password character rules | User registered with valid credentials; password rules enforced | 1. Go to Login page 2. Enter passwords violating rules: - Missing uppercase - Missing lowercase - Missing digit - Missing special character - Containing spaces 3. Click "Login" | Validation messages shown for each violated rule; login rejected | Not tested. Please, see comments. | Not executed | Tests not executed because signup validations already failed; any invalid credentials would not pass login, so testing is redundant. Will be tested after sign-up bugs (BUG-001, BUG-002) are fixed and retested successfully. | N/A
TC013 | Login - Case Sensitivity | User registered with valid credentials | 1. Open Login page 2. Enter username and password using different case combinations (e.g., all lowercase, all uppercase, mixed case) 3. Click "Login" | System treats credentials as case-sensitive: – Login succeeds only when username and password exactly match stored case – Login fails for incorrect case combinations with proper error message | Not tested. Please, see comments. | Not executed | Not tested for portfolio (out of portfolio scope) | N/A
TC014 | Login - Multiple Failed Attempts | User registered with valid credentials | 1. Open Login page 2. Enter valid username and invalid password 3. Repeat login attempt 5 times 4. Observe system response | After several failed attempts (5): – Account is temporarily locked or CAPTCHA appears – Proper message shown: “Too many failed attempts” | Not tested. Please, see comments. | Not executed | Not tested for portfolio (out of portfolio scope) | N/A
TC015 | Cart - add single product | User logged in | 1. Navigate to product page 2. Select a product 3. Click "Add to cart" | Product appears in cart with correct name, price, quantity and total | Product appeared in cart with correct name, price, quantity and totals as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC016 | Cart - add multiple products | User logged in | 1. Navigate to product page 2. Select and add to cart multiple products | All products appear in cart with correct name, price, quantity and total | All products appeared in cart with correct name, price, quantity and total as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC017 | Cart - add product not logged in | User not logged in | 1. Navigate to product page 2. Select a product 3. Click "Add to cart" | App handles gracefully: either allows guest cart or prompts login/register; behavior matches spec | Product was added to cart without guest cart or login/register prompt. Actual behavior deviates from expected. | Fail BUG-004 | Tested on Chrome 115, Windows 10 Note: No guest cart or login/register prompt appeared; potential usability/security issue | Screenshots/UI/BUG-004_TC_017_add_product_not_logged_in.PNG
TC018 | Cart - remove product | User logged in, product in cart | 1. Open cart 2. Select a product 3. Click "Delete" | Product removed from cart; cart updated; total recalculated correctly | Product was removed from cart; cart was updated; total recalculated correctly as expected Please see point for improvement in Comments | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! Note: No confirmation or prompt message displayed before item removal. This behavior might confuse users or lead to accidental deletions. Not reported as a defect for this project due to lack of specification, but noted as a potential usability improvement. | N/A
TC019 | Cart - update quantity | User logged in, product in cart | 1. Open cart 2. Change quantity: - Increment / decrement - Boundary values (min / max) 3. Observe line item price and total | Quantity changes reflected correctly; totals update; errors shown for invalid values | Feature not available – no quantity selector or update option present Please, see comments. | Fail BUG-005 | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! Note: Quantity selection feature not implemented; user can adjust quantity by adding/removing items. Usability impacted | Screenshots/UI/BUG-005_TC_019_change_quantity_in_cart_missing.PNG
TC020 | Checkout - valid flow | User logged in, cart not empty | 1. Open cart 2. Click "Place Order" 3. Fill Name, Country, City, Credit Card Number, Month, Year 4. Click "Purchase" | Order confirmation shown; cart cleared; purchase ID shown | Order confirmation was shown; cart was cleared; purchase ID was shown as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC021 | Checkout - missing required fields | User logged in, cart not empty | 1. Open checkout 2. Leave one of the fields empty: Name, Country, City, Credit Card Number, Month or Year 3. Click "Purchase" | Error message shown: "Please fill out Name and Credit Card"; order not placed | Error message was shown: "Please fill out Name and Credit Card"; order was not placed as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC022 | Checkout - invalid card / month / year | User logged in, cart not empty | 1. Enter invalid card (non-numeric, wrong length) 2. Enter month/year out of bounds 3. Click "Purchase" | Validation messages shown; order not placed | Validation messages were not shown; order was placed; system allowed invalid card details Please, see comments | Fail | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! Note: Actual test failed as system allowed invalid card details. Not creating a separate bug for portfolio purposes. Noted for awareness; would be reported in real project. | N/A
TC023 | Checkout - total amount verification | User logged in, cart not empty | 1. Add products with known prices 2. Open cart and note total 3. Complete purchase 4. Verify confirmation total | Total equals sum of item prices; no discrepancy | Total equals sum of item prices; no discrepancy as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
TC024 | Checkout - empty cart | User logged in, cart empty | 1. Open cart 2. Attempt to click "Place Order" | "Place Order" disabled or message: "Cart is empty"; order cannot be placed | Error message was not shown; order was placed; system allowed checkout with empty cart Please, see comments. | Fail | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! Note: Actual test failed; system allowed checkout with empty cart. Not creating a separate bug for portfolio purposes. Noted as potential usability issue. | N/A
TC025 | Checkout - order confirmation clears cart | After successful purchase | 1. Complete valid purchase 2. Open cart | Cart is empty after order; recent order confirmation visible | Cart was empty after order; recent order confirmation was visible as expected | Pass | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! | N/A
Additional Test Cases (Login Functionality). These test cases were created after initial execution to extend Login coverage.
TC026 | Login - Case Sensitivity | User account already registered with valid credentials | 1. Open Login page 2. Enter username and password using different case combinations (all lowercase, all uppercase, mixed case) 3. Click "Login" | System treats credentials as case-sensitive: login succeeds only when username and password exactly match stored case; login fails for incorrect case combinations with proper error message | System treated credentials as case-sensitive: login succeeded only when username and password exactly matched stored case; login failed for incorrect case combinations with proper error message as expected | Pass | Tested on Chrome 115, Windows 10. Username: testuser80/TestUser80/TESTUSER80 Password: 123321Mk!/123321mk!/123321MK! Note: Tested different combinations of username and password | N/A
TC027 | Login - Multiple Failed Attempts / CAPTCHA | User account already registered with valid credentials | 1. Open Login page 2. Enter valid username and invalid password repeatedly (e.g., 5 times) 3. Observe system response | After multiple failed attempts: account temporarily locked or CAPTCHA appears; proper warning message displayed | After multiple failed attempts: account temporarily was not locked or no CAPTCHA appeared; proper warning message was not displayed Please, see comments | Fail | Test failed; system allowed unlimited failed login attempts and no CAPTCHA was displayed. Not creating separate bug for portfolio purposes. Noted for awareness; would be reported in a real project (security impact). | N/A
TC028 | Session / Cookie Handling | User logged in | 1. Log in with valid credentials 2. Close browser tab without logging out 3. Reopen site 4. Observe session persistence and cookie handling | User session expires or persists according to system rules; cookies are handled securely; no unauthorized access allowed | Session did not expire as expected; cookies were not handled securely; unauthorized access was allowed Please, see comments | Fail | Test failed; session did not expire after logout / cookies not cleared. Not creating separate bug for portfolio purposes. Noted for awareness; would be reported in a real project (potential security risk). | N/A

## BugReport_UI
ID | Title | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Comments | Screenshot
BUG-001 | Password allows less than minimum characters | User not registered | 1. Open Signup 2. Enter username 3. Enter password (7 chars) 4. Click "Sign up" | Passwords below 8 chars rejected; valid lengths accepted | Successfully signed up with 7-character password; validation not shown | Medium | Medium | Tested on Chrome 115, Windows 10. Username: TestUser81 Password: 1234567 Note: boundary tests not fully executed for portfolio | Screenshots/UI/BUG-001_TC_005_Successful_sign_up_below_min_chars.PNG
BUG-002 | Password allows missing required character types | User not registered | 1. Open Signup 2. Enter username 3. Enter passwords violating rules: missing uppercase/lowercase/digit/special/contains spaces 4. Click "Sign up" | Signup rejected; validation messages shown for each violated rule | Successfully signed up with password missing required characters; validation messages not shown | Medium | Medium | Tested on Chrome 115, Windows 10. Username: TestUser81 Password: 1234567 Note: partial execution; portfolio practice | Screenshots/UI/BUG-002_TC_003_Successful_sign_up_missing_required_characters.PNG
BUG-003 | Username allows SQL/Injection-like characters | User not registered | 1. Enter username with SQL-like chars (e.g., or_1_eq_1_test2) 2. Click "Sign up" | App rejects invalid username; no server errors or DB injection | Successfully signed up with username containing SQL/Injection-like chars | High | High | Tested on Chrome 115, Windows 10. Username: or_1_eq_1_test2 Password: 12345678 | Screenshots/UI/BUG-003_TC_007_Successful_sign_up_SQL_Injection.PNG
BUG-004 | Cart allows adding items not logged in | User not logged in | 1. Navigate to product page 2. Select a product 3. Click "Add to cart" | App handles gracefully: either allows guest cart or prompts login/register; behavior matches spec | Product was added to cart without guest cart or login/register prompt. Actual behavior deviates from expected. | High | High | Tested on Chrome 115, Windows 10. Note: No guest cart or login/register prompt appeared; potential usability/security issue | Screenshots/UI/BUG-004_TC_017_Add_product_not_logged_in.PNG
BUG-005 | Quantity selection feature is missing in Cart | User logged in, product in cart | 1. Open cart 2. Change quantity: - Increment / decrement - Boundary values (min / max) 3. Observe line item price and total Note: Since feature doesn’t exist steps not executable; quantity selector missing | Quantity changes reflected correctly; totals update; errors shown for invalid values | Feature not available – no quantity selector or update option present Please, see comments. | Medium | Medium | Tested on Chrome 115, Windows 10. Username: TestUser80 Password: 123321Mk! Note: Quantity selection feature not implemented; user can adjust quantity by adding/removing items. Usability impacted | Screenshots/UI/BUG-005_TC_019_Change_quantity_in_cart_missing.PNG
BUG-006 | Layout of login form breaks (mobile view) | User opens site on mobile device or browser in responsive mode | 1. Open site 2. Open "Login" form 3. Switch to mobile view (e.g., iPhone 12 Pro in DevTools) 4. Observe layout of form fields | Form layout adapts to mobile view; all input fields and buttons visible and aligned correctly | Layout of login form breaks: fields overlap or extend beyond screen boundaries; misalignment observed | Medium | Medium | Tested on Chrome 115, Windows 10, Device / Viewport: iPhone 12 Pro (DevTools responsive mode) Note: Issue discovered during UI testing phase; not part of original Test Cases (out of scope) Note: Reported as example – similar layout issues occur in other input forms. Not creating separate bugs for portfolio; noted as recurring responsive design issue (UI/UX). | Screenshots/UI/BUG-006_Login_layout_breaks_mobile_view.PNG
BUG-007 | Embedded demo video fails to load | User is on the Home page of https://www.demoblaze.com DevTools Console is open. | 1. Open https://www.demoblaze.com 2. Open DevTools → Console 3. Observe video errors | Video loads and plays normally | Video fails to load. Console shows: -ERR_CONNECTION_TIMED_OUT -MEDIA_ERR_SRC_NOT_SUPPORTED | Medium | Low | Windows 10, Chrome 115 Note: Issue discovered during DevTools console analysis ; not part of original Test Cases (out of scope) | Screenshots/UI/BUG-007_Video_fails_to_load_About_us_error.PNG
BUG-008 | Console error on Cart page | User is on the Home page of https://www.demoblaze.com DevTools Console is open. | 1. Open https://www.demoblaze.com 2. Click the Cart tab in the top navigation menu 3. Open DevTools → Console 4. Observe the console output | Cart page loads correctly without JavaScript errors in the console | Cart page loads and functions normally, but console shows: "Uncaught ReferenceError: showcart is not defined at HTMLAnchorElement.onclick (cart.html:722:63)" | Low | Low | Tested on Chrome 115, Windows 10 Functionality unaffected; error likely due to unused or missing JS reference. Note: Issue discovered during DevTools console analysis; not part of original Test Cases (out of scope) | Screenshots/UI/BUG-008_Cart_showcart_not_defined.PNG

## TestCase_API
ID | Test Scenario | Method | Endpoint | Request Body (JSON) | Expected Result | Actual results | Status | Comments | Screenshot
TC_API-001 | Sign-Up – Success | POST | /signup | { "username": "TestUser88", "password": "MTIzMzIxTm4h" } | Status 200, empty body "" | 200 OK, empty body "" | Pass | User successfully created. Response saved as Example in Postman. | N/A
TC_API-002 | Sign-Up – User Already Exists | POST | /signup | { "username": "TestUser88", "password": "MTIzMzIxTm4h" } | Status 200, { "errorMessage": "This user already exist." } | 200 OK, { "errorMessage": "This user already exist." } | Pass | Duplicate user correctly handled. Validation works. | N/A
TC_API-003 | Sign-Up – Empty Username | POST | /signup | { "username": "", "password": "MTIzMzIxTm4h" } | Status 400, { "errorMessage": "Username required" } | 500 Internal Server Error | Fail (linked to BUG_API-001) | Server crash on empty username (unhandled input). Linked to BUG_API-001. | Screenshots/API/BUG_API-001_TC_API-005_Sign_up_empty_credentials_error_500.PNG
TC_API-004 | Sign-Up – Empty Password | POST | /signup | { "username": "TestUser89", "password": "" } | Status 400, { "errorMessage": "Password required" } | 200 OK, { "errorMessage": "This user already exist." } | Fail (linked to BUG_API-001) | No password validation; backend incorrectly checks duplicate user instead. Linked to BUG_API-001. | Screenshots/API/BUG_API-001_TC_API-005_Sign_up_empty_credentials_error_500.PNG
TC_API-005 | Sign-Up – Both Empty | POST | /signup | { "username": "", "password": "" } | Status 400, { "errorMessage": "Username and password required" } | 500 Internal Server Error | Fail (BUG_API-001) | Server crash on empty credentials (unhandled input). Response saved as Example (500 error). | Screenshots/API/BUG_API-001_TC_API-005_Sign_up_empty_credentials_error_500.PNG
TC_API-006 | Sign-Up – Invalid Characters | POST | /signup | { "username": "Test@User", "password": "1234" } | Status 400, { "errorMessage": "Invalid characters" } | Not tested | Fail (known UI issue) | UI test failed and confirmed that API accepts any characters — no character rules applied. Input validation missing globally. | N/A
TC_API-007 | Login – Success | POST | /login | { "username": "TestUser88", "password": "MTIzMzIxTm4h" } | Status 200, success message or token | 200 OK, Auth_token: VGVzdFVzZXI4ODE3NjA5NTk= | Pass | Token successfully generated and returned. Authentication endpoint works. | N/A
TC_API-008 | Login – Wrong Password | POST | /login | { "username": "TestUser88", "password": "WrongPass" } | Status 200, { "errorMessage": "Wrong password" } | 200 OK, { "errorMessage": "Wrong password." } | Pass | Negative test passed — API returns proper error message. | N/A
TC_API-009 | Login – Nonexistent User | POST | /login | { "username": "NoUser", "password": "MTIzMzIxTm4h" } | Status 200, { "errorMessage": "User does not exist" } | 200 OK, { "errorMessage": "User does not exist." } | Pass | Negative test passed — backend correctly handles nonexistent user. | N/A
TC_API-010 | Login – Empty Username | POST | /login | { "username": "", "password": "MTIzMzIxTm4h" } | Status 400, { "errorMessage": "Username required" } | 500 Internal Server Error (HTML) | Fail (linked to BUG_API-001) | Backend crash — unhandled empty username. Same issue pattern as Sign-Up (BUG_API-001). Linked to BUG_API-001. | Screenshots/API/BUG_API-001_TC_API-005_Sign_up_empty_credentials_error_500.PNG
TC_API-011 | Login – Empty Password | POST | /login | { "username": "TestUser88", "password": "" } | Status 400, { "errorMessage": "Password required" } | 200 OK, { "errorMessage": "Wrong password." } | Pass | Negative login scenario handled correctly. API returns appropriate error message. | N/A
TC_API-012 | Logout – Success | POST | /logout | Empty request body | Status 200, { "message": "Logout successful" } | 404 Not Found | N/A | /logout endpoint not implemented on Demoblaze API. Logout likely handled client-side (UI only). | N/A
TC_API-013 | Response Format Validation | Any | Any | N/A | Valid JSON, contains either success or errorMessage | /signup: valid JSON → OK; /login: plain text token (no JSON keys); /logout: non-JSON HTML | Partial Pass | Known issue: inconsistent response formats across endpoints (violates API response structure standard). No bug raised for demo API. Would be a bug in a real project. | N/A
TC_API-014 | Response Time | Any | Any | N/A | < 2 seconds | All requests completed under 2 s (verified in Postman) | Pass | Performance acceptable for all endpoints | N/A
TC_API-015 | Environment Variables Test | Any | Any | N/A | Variables {{base_url}}, {{username}}, {{password}} resolve correctly | All requests used correct base URL (https://api.demoblaze.com); variable {{base_url}} resolved successfully from environment and collection. | Pass | Environment and collection variables configured and active as expected | N/A
TC_API-016 | Test Script Validation | Any | Any | N/A | Postman test confirms correct success/error message | Collection-level script executed for all requests; detected 500/404 errors and skipped non-JSON cases correctly | Pass | Automation script works as intended; accurately reports server errors and response type | N/A
TC_API-017 | Add item to cart – success | POST | /addtocart | { "id": "fa1c9918-875d-c378-3035-f5c2a772f861", "cookie": "VGVzdFVzZXI4MDE3NjEyMDE=", "prod_id": 2, "flag": true } | 200 OK | 200 OK | Pass | Validated with real token and product ID captured from DevTools. Response 200 OK, empty body (expected for demo API). | N/A
TC_API-018 | Add to Cart – Invalid Product ID | POST | /addtocart | { "id": "fa1c9918-875d-c378-3035-f5c2a772f861", "cookie": "VGVzdFVzZXI4MDE3NjEyMDE=", "prod_id": 999999, "flag": true } | Status 400 or error message { "errorMessage": "Invalid product ID" } | Status 200 OK, empty body; response time 7207 ms | Fail (BUG_API-002) | Product ID not validated by backend; server accepted invalid product. Response time exceeded 2 s limit. | Screenshots/API/BUG_API-002_TC_API-018_Server_accepted_invalid_product_id.PNG
TC_API-019 | View Cart – Success | POST | /viewcart | { "cookie": "VGVzdFVzZXI4MDE3NjEyMDE=", "flag": true } | 200 OK, JSON list of items | Status 200 OK, {"Items": []} | Partial Pass (Environment limitation – expected behavior in demo setup) | Response successful but cart data not persisted outside browser session (demo API limitation). Cart data is session-based — items are visible only during the active UI session and disappear after page refresh or navigation. Verified that Demoblaze demo backend maintains cart state only within an active browser session; the token is not reusable externally. Expected behavior for the demo environment — no bug raised. | N/A
TC_API-020 | Delete item from cart – success | POST | /deleteitem | { "id": "8fbeb8ed-ce60-d0d0-1bff-ffe856139fd3" } | Status 200 OK, JSON { "success": true } | Status 200 OK, { "errorMessage": "Not found." } | Partial Pass (Environment limitation – expected behavior in demo setup) | Response successful but cart data not persisted outside browser session (demo API limitation). Cart data is session-based — items are visible only during the active UI session and disappear after page refresh or navigation. Verified that Demoblaze demo backend maintains cart state only within an active browser session; the token is not reusable externally. Expected behavior for the demo environment — no bug raised. | N/A
TC_API-021 | Place order – success | POST | /placeorder | { "name": "Test User", "country": "Israel", "city": "Tel Aviv", "creditCard": "1234-5678-9999-0000", "month": "10", "year": "2025" } | 200 OK, order ID returned (e.g., { "orderId": 12345 }) | 404 Not Found | Partial Pass (Environment limitation – expected behavior in demo setup) | Endpoint not implemented in demo backend; checkout simulated only on UI. Expected limitation of demo API — no bug raised. | N/A
TC_API-022 | Place order – missing payment details | POST | /placeorder | { "name": "Test User" } | 400, { "errorMessage": "Payment details required" } | 404 Not Found | Partial Pass (Environment limitation – expected behavior in demo setup) | Endpoint not implemented in demo backend; checkout simulated only on UI. Expected limitation of demo API — no bug raised. | N/A
TC_API-023 | Place order – invalid card format | POST | /placeorder | { "creditCard": "abcd" } | 400, { "errorMessage": "Invalid card number" } | Not tested | Not Tested | Endpoint not implemented; all negative cases return 404 Not Found — same as TC_API-022. | N/A
TC_API-024 | Response validation | Any | Any | N/A | Valid JSON with success or errorMessage; under 2s response | All requests passed validation; 1 skipped due to HTML (non-JSON) response (known backend issue), all others valid and < 2 s | Pass | Automation script works as intended; accurately reports server errors and response type | N/A

## BugReport_API
ID | Title | Method | Endpoint | Request Body (JSON) | Expected Result | Actual results | Severity | Priority | Comments | Screenshot
BUG_API-001 | Sign-Up with empty credentials cause 500 error | POST | /signup | { "username": "", "password": "" } | Status 400, { "errorMessage": "Username and password required" } | 500 Internal Server Error | High | Medium | Server crash on empty credentials (unhandled input). Response saved as Example (500 error). Note: Detailed reproduction steps available in Jira ticket. | Screenshots/API/BUG_API-001_TC_API-005_Sign_up_empty_credentials_error_500.PNG
BUG_API-002 | Add to Cart – Invalid Product ID | POST | /addtocart | { "id": "fa1c9918-875d-c378-3035-f5c2a772f861", "cookie": "VGVzdFVzZXI4MDE3NjEyMDE=", "prod_id": 999999, "flag": true } | Status 400 or error message { "errorMessage": "Invalid product ID" } | Status 200 OK, empty body; response time 7207 ms | High | Medium | Product ID not validated by backend; server accepted invalid product. Response time exceeded 2 s limit. | Screenshots/API/BUG_API-002_TC_API-018_Server_accepted_invalid_product_id.PNG